## mundijong timeline
Animation Timeline
Project Name: Mundijong Road Extension
Project type: Animation Video
Project details: 2 to 3 Min Animation
Project start date: 22 Feb 13 | Date | Working days
Initial Briefing Meeting | 2013-02-22
Preparing and finalising the brief / storyboard | 2013-02-22 | 1 Day
Stage 1 - Basic 3D Modelling
Basic modeling ( 50% ) | 2013-02-26 | 3 Days
Client Feedback ( Stills will be provided ) | 2013-02-26 | Same Day
Revisions if any | 2013-02-26 | Same Day
Stage 2 - Detailed 3D Modelling
Detailed modelling |  | 3 Days
Applying Lighting |  | 1 Day
Adding other items like signage etc
Adding landscaping
Applying texture maps to model
Applying colours to model | 2013-03-01
Client Feedback | 2013-03-01 | 1 Day
Revisions if any | 2013-03-02 | 1 Day
Stage 3 - Camera Pathway
Setting up Camera : Working on camera movements, speed and positioning |  | 2 Days
Adding people |  | 2 Days
Camera pathway preview ( Viewport preview )
Provide stills of nth frames | 2013-03-08
Client Feedback | 2013-03-11 | 1 Day
Revisions if any | 2013-03-12 | 1 Day
Stage 4 - Rendering of Animation
Final Hi Res Rendering ( Std HD Format : 1280 x 720 p ) ( 30 Frames / Sec ) | 2013-03-19 | 6 to 8 Days
Stage 5 - Post Production
Compositing ( Adding Music, Voice Over, Logos, Video footage, 2D Work, Text, Google Earth | 2013-03-21 | 2 Days
Final Delivery to Client | 2013-03-21
NOTE: The above schedule is based on the assumption that we are in receipt of the required information in time. This also includes client feedback time and will vary if there is delay in feedback from the clients side.